## Project Analysis & Plan
Ondeck, Inc.
Platform to connect homeowners with home improvement professionals
Project Overview
Corey Geer is looking to build a platform to compete with Homeadvisor and disrupt the online home improvement listings space.
Corey has experience in this industry. His model is superior to the existing market because it utilizes a network of local connectors (TLCs) to build relationships with contractors.
Ondeck will provide superior value to homeowners by making sure contractors have proper insurance and providing local mediation if a job has issues.
Ondeck's pricing structure (only charge contractors for real jobs) is more advantageous for contractors than existing market offerings (charge per lead). Eliminates noise- creates a word-of-mouth referral.
VC investors have shown interest in the platform. Corey's investors are particularly interested in bringing jobs to Traverse City.
Corey is looking to move fast (alpha tests in Spring 2018) to pilot his platform, demonstrate success to potential investors, and gather learnings to inform subsequent full-scale buildout.
Corey already has TLCs and contractors eager to be part of his pilot program in Traverse City.
Corey has reached out to Atomic Object for help with building the platform.
Atomic has the technical expertise and the right process to set the architecture directon for the platform and get an MVP to market quickly, as well as help Corey hire a technical team and onboard them into agile development practices and modern web technologies.
After talking with Corey, Atomic Object recommends a phased approach to building out the platform.
Phase 1 will focus on the consumer (homeowner)-facing experience. It is meant to grow a user base of homeowners and contractors, and gather learnings that will inform later phases of building out more robust tools for Trusted Local Connectors (TLCs) and contractors.
For a technical approach, Atomic recommends leveraging a modern frontend framework (for example React.js or Ember) coupled with a Ruby on Rails backend with ActiveAdmin as a shim for a minimal TLC interface that will support early learnings and be replaced in later phases of development. Using popular tools will help with recruiting and onboarding a team.
During this phase, manual process or third-party tools will be favored for some functionality before scaling the business.
Project Goals
1.) Launch a robust homeowner-facing website in 1-3 local test markets (Traverse City, Grand Rapids, ??) to build valuable local contractor network and prove market fit.
2.) Start with a minimal TLC/Contractor experience in order get to market quickly and learn about TLC behaviors and needs.
3.) Use learnings to inform design and buildout of TLC portal in later phases of product development.
| Common Project Considerations | Concern Exists | Notes
Organizational software development experience and capabilities
Legacy or immature technologies (lack of tooling power)
Regulatory requirements
Complex and/or regulated deployment process
Amount/alignment of project stakeholders (many is difficult, one decision owner is ideal)
Integrations with external systems
Amount of technology domains (e.g. web, mobile, desktop, embedded) involved
Migration needs from prior production versions
Criticality to business operations
Potential for hidden/emerging requirements
Product-market fit
Project value to organization
Recommended Project Plan
Atomic will work with Corey for a ~1 month Research, Design, and Planning phase focused on building a detailed deveopment plan so that the team can act fast.
Wireframes and prototypes will help articulate and hone intended functionality. Style tiles and key interface mockups will be used to quickly establish a visual approach.
Atomic and Corey will work for ~4-5 months to build homeowner-facing website and minimal contractor / TLC tools to support the pilot.
There would be potential for Atomic to help Corey vet and train technical staff during this period.
Based on insights and outcomes of the pilot, Atomic can re-engage in the future for additional product development to support scaling and enhancing the user experience.
Please see additional resources to better understand Atomic's approach to budgeting, engagement management, and process:
Process overview
Setting and managing budget
Software project budgeting is more than estimating
Kicking off the project ¦ Research, Design, & Planning
When should a startup hire a software consultant?

## Budget & Timeline Overview
Budget and Timeline Overview
Hourly Rate | 140
Rounding Multiple | 10000
Budget Model | Budget | Rounded Budget (Nearest $10,000) | Project Duration (Weeks) | Notes
Educated-guess Budget Model (3 months) | 202272 | 200000 | 13 | Assumes ideal team model. Uses simple gut feeling team model.
Educated-guess Budget Model (5 months) | 337120 | 340000 | 22 | Assumes ideal team model. Uses simple gut feeling team model.
Comparable-project Budget Model | 332500 | 330000 | 22 | Assumes ideal team model. Uses simple gut feeling team model.
Bottom-up Budget Model | 45360 | 50000 | 4 | Assumes ideal team model. Uses phased bottom-up team model.
Likely budget range | $300,000-$350,000
Phase 1 budget target | Identify this with Corey's input

## Educated Guess
Educated-guess Budget Model
Team Model | Hours/Week
Development Lead | 36
Developer | 36
Design Lead | 18
Delivery Lead | 18
Exploratory Tester | 4
Approximate team hours/week | 112
Approximate weekly cost | 15680
Months | Budget
3 | 202272
5 | 337120

## Comparable Project
Comparable-project Budget Model
Type of Project:
Responsive-Web project with React.js frontend and Ruby on Rails Backend
Key Functionality of comparable project:
Early-Stage Startup - "Uber for nursing"
Alpha / pilot release to prove concept and unlock more funding
Consumer-facing app connecting those in need of specific nursing home care tasks with mobile nurses to provide the service
ActiveAdmin backend for reporting & management/admin workflows
Consumer signup is self serve; nurse onboarding is completely manual (accomplished via ActiveAdmin)
lightweight reviews- "thumbs up"/"thumbs down"
Actual Time Spent:
| Function | Approximate Hours | Percentage
| Development | 1050 | 72.41%
| Design | 200 | 13.79%
| Delivery | 200 | 13.79%
| Total hours | 1450
| Cost @ $140/hr | 203000
Differences:
| Difference | More / Less
| consumers limited to only 7 nursing services | Less
| Limited alpha release - expect <100 users for initial pilot - not optimized for more traffic | Less
| Regulated environment - HIPAA compliance | More
| users cannot browse/choose nurses | Less
| provided their own FTE developer to work with the team | Less
| Visual branding and marketing site handled by another firm | Less
Gut Feel Correction:
| Function | Approximate Hours | Percentage | Note
| Development | 1575 | 66.32% | Ondeck phase 1 is slightly larger, and the client provided a solid developer whose hours aren't included above.
| Design | 400 | 16.84% | Atomic is handling more design.
| Delivery | 400 | 16.84% | Expect Delivery and Design time to be roughly equal for Ondeck.
| Total hours | 2375
| Cost @ $140/hr | 332500
| Comparable Project | 332500

## Bottom-up
Bottom-up Budget Model
Summary
Phase | Budget | Estimated Weeks
Research, Design, and Planning | 45360 | 4
Implementation | 0 | 0
Budget | 45360 | 4
Research, Design, and Planning
Week | Developer Hours | Designer Hours | Delivery Lead Hours | Work
Week 1 | 0 | 36 | 36 | Collaborative Kickoff, Branding Workshop, key workflows, begin wireframes
Week 2 | 0 | 36 | 36 | continue wireframes & key workflows
Week 3 | 0 | 36 | 36 | Refine wireframes, style tiles, key interface mockups
Week 4 | 36 | 36 | 36 | Finalizing visual & functional design, detailed backlog & estimation, core application infrastructure & deployment
Total hours (rounded up) | 36 | 144 | 144
Calendar weeks | 4
Budget | 45360
Implementation
Team Model | Hours/Week
Development Lead | 36
Developer | 36
Design Lead | 18
Delivery Lead | 18
Exploratory Tester | 4
Approximate team hours/week | 112
Approximate weekly cost | 15680
Work | ABP (Developer Days) | HP (Developer Days) | Buffer Term | Notes
HOMEOWNER EXPERIENCE
Find a Contractor
View Homepage for my market
Search by service needed
View contractor's portfolio page
Book a Job
Pay Booking Fee or apply previously paid fee
CONTRACTOR MVP
Subtotal developer days (rounded up) | 0
Buffer developer days (rounded up) | 0
Developer days | 0
Average developer hours/week | 72
Calendar weeks | 0
Budget | 0
Estimate Key
Range Estimates
ABP - Aggressive But Possible Estimate
HP - Highly Probable Estimate